## Sheet1
Story Report
Team | Ticket ID | Description | Type | Approach | Approach Reviewer | Hrs | CR Comment | CR Round | QA Round | Bugs Found | Start Date | End Date | Remarks
Orange | YES-1397 | Campaign Set-Up: Multi-Select Touchpoint addition and removal | Story | Using the same approach as YES-2083 | Greg Talerico | 30 | 1 | 1 | 2 | 0 | 2018-03-30 | 2018-04-05
Orange | YES-2648 | Expose user divisions via Yesmail-Messenger | Story |  | Ben Sheifer | 4 |  |  |  |  | 2018-04-04 |  | Stuck because whenever we are taking latest pull fom develop E8 and auth.js is breaking